ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	4

2.1.	Overall objective	4

2.2.	Purpose	5

2.3.	Results to be achieved by the Contractor	5

3.	ASSUMPTIONS & RISKS	5

3.1.	Assumptions underlying the project	5

3.2.	Risks	5

4.	SCOPE OF THE WORK	5

4.1.	General	5

4.2.	Specific work	6

4.3.	Project management	16

5.	LOGISTICS AND TIMING	16

5.1.	Location	16

5.2.	Start date & Period of implementation of tasks	16

6.	REQUIREMENTS	16

6.1.	Staff	16

6.2.	Office accommodation	18

6.3.	Facilities to be provided by the Contractor	18

6.4.	Equipment	18

7.	REPORTS	18

7.1.	Reporting requirements	18

7.2.	Submission and approval of reports	19

8.	MONITORING AND EVALUATION	19

8.1.	Definition of indicators	19

8.2.	Special requirements	19

- BACKGROUND INFORMATION

## 1.1 Partner country

Serbia

## 1.2 Contracting authority

Statistical office Republic of Serbia

## 1.3 Country background

The Instrument for Pre-Accession Assistance (IPA) 2022 National Programme has the overall objective of enabling the Serbian administration to effectively meet EU accession requirements and successfully manage EU pre-accession assistance geared toward EU membership. Its specific objective is to upgrade the statistical system and enhance the comparability and interconnectivity of statistical data.

## 1.4 Current situation in the sector

## The Statistical Office of the Republic of Serbia (SORS) is the lead institution holding the primary responsibility as the principal producer and disseminator of official statistics. It serves as the professional custodian, organizer, and coordinator of the official statistics system, presenting the official statistics of the Republic of Serbia within the international statistical framework. One of its main strategic objectives is to complete harmonization of the statistical standards and practice with the European Statistical System (ESS) and the European Union. Over the years and with assistance from the EU and other funds, SORS has made significant steps towards full compliance with the EU regulations in a number of statistical areas. However, more needs to be done in this direction. The global objective of the project is to continue the process of modernization of the Serbian statistical system and support its full harmonisation with the ESS.

## The Law on the Official Statistics delineates the legal framework governing the SORS’ access and utilization of external information sources: SORS is granted the right of access to administrative data and to participate in all activities related to the establishment or modification of administrative data sources. In the Law, it is explicitly stated that the SORS, acting as the coordinator of the statistical system, not only possesses the authority to access all administrative data but also holds influence over methodological solutions in administrative registries and databases.

## Even though SORS provides technical solutions and coordinates activities around the development of the components of the project, the effectiveness of the initiative is in correlation with the quality of administrative and statistical data integrated in the system.

## Consequently, beyond this institutional mandate, SORS is fully committed to fostering good relationships with data owners and to facilitating extensive experience and support to uphold or enhance data quality. Effectively utilizing external data hinges on establishing collaborative working connections between SORS and data providers: efficient cooperation is indispensable for ensuring the long-term suitability of data sources for DMSS.

## Signing cooperation contracts or service level agreements provides optimal support for the project. These agreements help ensure the commitment of each institution is more structured beyond the general mandates required by law, and the roles and responsibilities are clearly defined and bound by a concrete time frame. In awareness of this, SORS is actively working to enhance the integration of administrative data by forging additional formal cooperation agreements for data transfer or exchange. This will help clarify roles and responsibilities, thereby strengthening the foundation for effective partnership and data sharing.

## 1.5 Related programmes and other donor activities

The SORS has received significant support from the EU with an aim to strengthen the national statistical system and take forward its integration into the European Statistical System (ESS) and make it compliant with the Eurostat Code of Practice (CoP). The EU support to SORS was based on national and multi-beneficiary IPA programme projects. This Action provides continued and complementary support to the results already achieved through these projects.

Beside the EU support to statistics, SORS has continual bilateral cooperation with various statistical offices and institutions, such as the French National Institute of Statistics and Economic Studies (INSEE). The cooperation covers various statistical fields of particular importance for SORS (using the administrative sources of data for different needs, exchanging the experiences, etc.). Observing their long-standing experience and tradition in econometric modelling, indicator design, and providing the decision-makers with various econometric analyses and studies in the form of short, easily digestible, information has had a significant effect in SORS' approach and motivation to provide decision-making

With the support of numerous IPA Multi-beneficiary programmes, the quality of labour market related statistics was significantly improved by applying international methodologies, definitions and classifications, while data collection methods were modernized and sample size increased. The following projects provided SORS with the valuable knowledge and experience that will be applied in this Action:

•	The development of the “Short-term business statistics (STS)” through several IPA Multi-beneficiary statistical cooperation programme cycles (IPA MB 2012, IPA MB 2014, IPA MB 2015, IPA MB 2017, IPA MB 2019) has included collection, the development and testing of various high-frequency indicators. This has significantly enriched the available data for high-frequency reports.

•	The development of the “Macroeconomic Imbalance Procedure (MIP)” indicator system through two IPA Multi-beneficiary statistical cooperation programme cycles (IPA MB 2014, IPA MB 2015, IPA MB 2017) provided an opportunity to learn about composite macroeconomic indicator creation, systems of such indicators and the early-warning detection on top of them. This work will be incorporated in the decision-making support activities.

•	The experience with the cooperation with different institutions, as well as integrating multiple data sources, including administrative data, has been gained through several different previous projects, such as "Interoperability - Joined Up Data for Joined Up Government" (IPA 2015 Multi-beneficiary statistical cooperation programme). This project has reinforced and encouraged general policy on data access and use of administrative data and improved general institutional environment and communication policy. Good cooperation with a few administrative data holders has been established. As a result of conducted activities within this project there is improved interoperability which has the following consequences: 1) Improved cooperation with Tax Authority (TA data are used for the calculation of average wages and salaries from January 2018.) 2) Improved cooperation with Ministry of the Interior - obtained data on residence/temporary residence for all Serbian citizens, 3) Improved cooperation with Ministry of Justice - agreement was made to switch to electronic data transmission of statistical surveys related to crime statistics and statistics on divorces, 4) Improved cooperation with the Ministry of Public Administration and Local-Self Government concerning electronic data transmission of statistics of births, deaths and marriages, 5) Improved cooperation with Republic Geodetic Authority - participation in WG for constitution of the Addresses Register. Most of the data obtained from administrative sources will be integrated into the LMIS. To this goal contributed also the project "Integrated data and information management of social protection benefits and other types of income" (IPA 2017 Multi-beneficiary statistical cooperation programme). This experience, as well as having some already available data, will be very relevant in the process of collecting and processing data for the decision-making support platform.

•	In the scope of IPA 2014 Multi-beneficiary Statistical Cooperation Programme the Ad hoc project was „Developing Job Vacancy Statistics “, carried out with the aim of identifying administrative sources and surveys which may have information on JVS. The result is that there are no comprehensive and complete sources for obtaining data on Job Vacancy. Experience gathered during the study visit helped to establish the decision that JVS data can be obtained by involving private employment agencies, in addition to the NES, in the reporting process.

The SORS has received significant support from the EU for the alignment with the EU requirements in the field of statistics, through aligning present methodologies and outputs with the statistical acquis and taking forward its integration into the European Statistical System.

With support of the IPA 2011 Direct Grant for the “Alignment with the European Statistical System”, SORS had successfully conducted the 2011 Census of Population, Households and Dwellings. This implemented action reached the predefined objectives and results, which present the backbone for all further statistical activities.

Initially, the possibilities of establishing SPR based on all relevant administrative sources were tested within the IPA 2012 - Statistical Population Register. Although the results shown that there are still no basic conditions for creating and updating the Statistical Population Register and for implementation of the fully register based census in the Republic of Serbia, the efforts were made to ensure cooperation with relevant authorities/institutions in the Republic of Serbia, review the actual situation and provide all required elements for defining the implementation method for the next Population Census.

Within IPA 2015 Multi-country statistical cooperation programme, an ad-hoc project “Pilot Population Census” had been conducted in April 2019 on the sample of 260 enumeration areas (about 20,000 households and 50,000 persons). All methodological and organisational solutions, including new data collection techniques, were tested, so they could be applied in the 2022 Census.

Activity within the project IPA 2018 National Programme - EU for Development of Statistics in Serbia and the largest component within, the 2022 Census of Population, Households and Dwellings, also aims at improving the basis for introduction of a register-based census. Activity 1.4: Strengthening of capacities relevant public administration bodies for introduction of the register-based census in 2031 precedes the establishment of the Statistical Population Register. The final stage of this activity is development of the Action plan for introduction of the register-based census in the Republic of Serbia and identifying all public administration bodies relevant for this activity.

All the a fore mentioned assistance in the previous period significantly contributed to the current level of SORS development, which is reflected in the annual reports of the European Commission, as well as in various Eurostat reports. Accumulated previous experiences and knowledge represent the sound grounds for the successful project implementation. In addition to the improvement of various statistical fields, previous EU assistance has significantly contributed to strengthening the managerial capacity of SORS to manage large and complex projects such as this Action.

- OBJECTIVE, PURPOSE & EXPECTED RESULTS

## 2.1 Overall objective

The overall objective of the project, of which this contract will form a part, is as follows:

- To support the organization of seminars (including accommodation, meals, transportation, conference rooms, and interpreters),

- To purchase plain tickets for SORS staff during the project,

- To provide hotel accommodation for SORS staff during the fieldwork phase,

- To arrange transportation and accommodation for SORS staff abroad for study visits and course attendance,

- To offer catering services for workshops,

- To provide other related services as requested by users for the needs of the Statistical Office of the Republic of Serbia during the implementation of the IPA 2022 EU4SORS project.

## 2.2Purpose

The purpose of this contract is to support the organization of seminars (including accommodation, meals, transportation, conference rooms, and interpreters), provide hotel accommodation for SORS staff during the fieldwork phase, arrange transportation and accommodation for SORS staff abroad for study visits and course attendance, offer catering services for workshops and meetings, and provide other related services as requested by users for the needs of the Statistical Office of the Republic of Serbia during the implementation of the IPA 2022 EU4SORS project.

## 2.3Results to be achieved by the contractor

## Successfully organized seminars, catering services for workshops and meetings, hotel accommodation, transportation, plain tickets and other related services at the request of users for the needs of the Statistical Office of the Republic of Serbia, ensuring a certain degree of flexibility to facilitate the attendance of the highest number of target participants, as requested by the Contracting Authority.

- ASSUMPTIONS & RISKS

## 3.1Assumptions underlying the project

The engaged agency shall the experience  necessary for the successful action realization.

•	A sufficient number of invited bidders shall apply to the offer.

## 3.2Risks

Given the nature of the action no major risk are identified.

- SCOPE OF THE WORK

## 4.1General

### Description of the assignment

### The purpose of this contract is to support the organization of seminars (including accommodation, meals, transportation, conference rooms, and interpreters), provide hotel accommodation for SORS staff during the fieldwork phase, arrange transportation and accommodation for SORS staff abroad for study visits and course attendance, offer catering services for workshop and meetings, and provide other related services as requested by users for the needs of the Statistical Office of the Republic of Serbia during the implementation of the IPA 2022 project.

### Geographical area to be covered

Serbia and Europe

### Target groups

## The main target groups are stakeholders (local governments, regional chambers of commerce, ministries, and other institutions), interviewers, and experts from SORS.

## 4.2 Specific work

The contractor will be responsible for.

Purchase plain tickets, maximum specification:Table 4.2

| Destination | Number | Class |
| --- | --- | --- |
| Total | 70 | Economy |
| Madrid | 10 | Economy |
| Brussels | 5 | Economy |
| Athena | 5 |  |
| Helsinki | 5 | Economy |
| Paris | 10 | Economy |
| Valeta | 5 |  |
| Viena | 5 |  |
| Rome | 10 | Economy |
| Lisbon | 15 | Economy |

Plain tickets must be return

Plain tickets must be return economy class tickets (and must include airport tax and, where appropriate, any charges for making the tickets available for collection at the airport of departure

Changes and cancellations

The Contractor must provide participants with the necessary assistance whenever changes must be made to tickets. Also, the Contracting Authority must be immediately notified of any major changes to flight times and its prior approval of such changes must be obtained. The Contractor must take whatever steps are necessary to ensure that any requests for cancellation are settled in the best interest of the Contracting Authority. Any additional outlay owing to negligence attributable to the Contractor will be borne by the latter. If a participant buys his own ticket or decides not to participate, he shall notify the Contractor in due time to prevent the latter from any unnecessary costs. If he does not do so, the unused ticket bought by the Contractor is an eligible cost, less the amount which has been reimbursed, if possible. In case of "no show" of participants, cancellation costs are eligible.

Delivering tickets

As a general rule the Contractor will book e-tickets and prepaid tickets for participants. If this is not feasible, the Contractor will contact participants to make arrangements for sending tickets or making them available for collection at the airport of departure.

If the plain  tickets which are not listed in the specification purchased, a special offer will be requested for each such case.

Providing hotel accommodation, maximum specification: Table 4.2

| Destination | Travelers | Nights | Description |
| --- | --- | --- | --- |
| Total | 70 | 210 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |
| Madrid | 10 | 30 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |
| Brussels | 5 | 15 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |
| Athens | 5 | 15 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |
| Helsinki | 5 | 15 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |
| Paris | 10 | 30 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |
| Valeta | 5 | 15 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |
| Vienna | 5 | 15 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |
| Rome | 10 | 30 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |
| Lisbon | 15 | 45 | Hotel minimum 3 stars, located in the center preferebly near national statistical offices |

Night with the breakfast is obligatory.

Insurance for all travelers in reqeuired cities and countries for 210 days is obligatory.

4.2.1 The Contractor is in charge of organizing supervising and following up the whole event.

The contractor will be responsible for organization workshop, conference, study visits, Course, seminar/trainer as follows. The requested services will include the organisation of accommodation, pansion with meals, catering, local transports, meetings, set up for selected participants.

Joint events for the Decision-making Support System (DMSS NL, DMSS LL and LMIS)

Closing conference

For the Closing coference the contractor will organize one 2-day conference for 300-350 participants in December 2027 within 300 km from Belgrade.

It is necessary to arrange transportation and full-board accomodation for 2 nights for all participants.

At the venue the contractor is obligated to provide technical conditions for the workshop: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), ensuring high-quality internet connectivity, setup of necessary audio-visual equipment (projectors, microphones, screens, speakers, etc.), on-site technical support to handle equipment and troubleshooting.

It is necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, juice) for each day.

4.2.1.1 Requested services for the Decision-making Support System at the National level (DMSS NL)

1.Professional methodological workshop for DMSS NL

For the Professional methodological workshop for subcomponent DMSS NL the contractor will organize one 5-day workshop for 150-200 participants in June 2025 within 300 km from Belgrade.

It is necessary to arrange transportation and full-board accomodation for 4 nights for all participants.

At the venue the contractor is obligated to provide technical conditions for the workshop: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), ensuring high-quality internet connectivity, setup of necessary audio-visual equipment (projectors, microphones, screens, speakers, etc.), on-site technical support to handle equipment and troubleshooting.

It is necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, juice) for each day.

2.Training of researchers for DMSS NL survey

For the Training of researchers for DMSS NL survey the contractor will organize one 4-day training for 40-80 participants in September 2025 within 300 km from Belgrade.

It is necessary to arrange transportation and full-board accomodation for 3 nights for all participants.

At the venue the contractor is obligated to provide technical conditions for the training sessions: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), ensuring high-quality internet connectivity, setup of necessary audio-visual equipment (projectors, microphones, screens, speakers, etc.), on-site technical support to handle equipment and troubleshooting.

It is necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, juice) for each day.

3.Training of users for DMSS NL web portal

For the Training of users for DMSS NL web portal the contractor will organize one 5-day training for 150-200 participants in November 2027 within 300 km from Belgrade.

It is necessary to arrange transportation and full-board accomodation for 4 nights for all participants.

At the venue the contractor is obligated to provide technical conditions for the workshop: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), ensuring high-quality internet connectivity, setup of necessary audio-visual equipment (projectors, microphones, screens, speakers, etc.), on-site technical support to handle equipment and troubleshooting.

It is necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, juice) for each day.

4.Study visits

For the DMSS NL study visits, the contractor will organize five 3-day study visits in five different countries during 2025 and 2026, each for 5 participants. The contractor will be responsible for arranging transportation, accommodation, and insurance for all participants, covering a total of 4 nights per visit.- Listed in tables 4.2

5.Courses

For the international courses, the contractor will organize transportation, accommodation, and insurance for the courses taking place from 2025 to 2027.

Requested services for the Decision-making Support System at the Local level (DMSS LL)

1. Initial workshop with SORS staff from regional offices

For the Initial workshop with SORS staff from all regional offices, heads of departmens and methodologists, regarding of organization of upcoming activities on the DMSS LL development, contractor will organize two day workshop in June 7th - 9th 2025. Workshop will attend 43 participants for two days . For the meeting, it is necessary to arrange transport from Belgrade for around 20 persons and full board accommodation for 2 nights for all participants. At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel) with enough table seats for all participants, audio equipment and video projection devices. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

2.Initial workshop with IT staff

For the Initial workshop with IT staff, regarding of organization of upcoming activities on the DMSS LL development, contractor will organize two day workshop in June 14-16th 2025. Workshop will attend 37 participants for two days. For the meeting, it is necessary to arrange transport from Belgrade for around 25 persons and full board accommodation for 2 nights for all participants. At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel) with enough table seats for all participants, audio equipment and video projection devices. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

3.Training field researchers/in depth interviewers for the pilot

For the training of field researchers/in depth interviewers for the pilot - preparation for field activities, contractor will organize one day training in jun 04-05th 2025. Training will attend 36 participants. At the venue contractor is obliged to provide 1 full-board accommodation for participants, conference room usage with tables, speed internet and a sufficient number of standard power sockets for connecting laptops to electricity during work, coffee breaks (coffee, tea, water, juice), water in the work rooms, and travel expenses.

4.Workshop with SORS heads of regional departments and methodologists, after pilot survey

For Workshop with SORS heads of regional departments, and methodologists, after pilot survey contractor will organize the 2-day workshop. Workshop will attend 43 participants for two days on august 27-29th 2025. For the meeting, it is necessary to arrange full board accommodation for 2 nights for all participants. At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel) with enough table seats for all participants, audio equipment and video projection devices. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

5.Workshops with municipalities and regional chamber of commerce after a pilot surveys – top management

For the workshops with municipalities and regional chamber of commerce contractor will be organized two day workshop in 6 locations in first two weeks in September 2025.  with the participation of top management from local governments and regional CCIS offices, involving around 280 people (approximately 40-50 persons per location). For the meeting, it is necessary to arrange full board accommodation for 1 night for all participants.  At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities, audio equipment and video projection devices. It is also necessary to provide bottled water during the work and two coffee breaks (coffee, tea, water, juice) for each location.

6.Workshops with municipalities and regional chamber of commerce after a pilot surveys – operative staff

For the workshops with municipalities and regional chamber of commerce contractors will be organized two-day workshop in 6 locations in in first two weeks in September 2025.  with the participation of heads of social, economic and environment departments - operative staff from local governments and regional CCIS offices, involving around 280 people (approximately 40-50 people per location). For the meeting, it is necessary to arrange full board accommodation for 1 night for all participants.  At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities, audio equipment and video projection devices. It is also necessary to provide bottled water during the work and two coffee breaks (coffee, tea, water, juice) for each location.

7. Workshop with SORS staff, for upcoming activities for the main survey.

For the workshop with SORS staff, for upcoming activities for the main survey contractor will organize two-day workshop for 43 persons on October 6-8th 2025. For the meeting, it is necessary to arrange transport from Belgrade for around 20 persons and full board accommodation for 2 nights for all participants. At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities with enough table seats for all participants, audio equipment and video projection devices. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

8.Workshop with IT staff, for upcoming activities for the main survey.

For the workshop with IT staff, for upcoming activities for the main survey contractor will organize two-day workshop for 37 persons on October 8-10th 2025 in the same location as the previous workshop with SORS stuff. For the meeting, it is necessary to arrange transport from Belgrade for around 25 persons and full board accommodation for 2 nights for all participants. At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities with enough table seats for all participants, audio equipment and video projection devices. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

9.Training of field researchers/in depth interviewers for one domain, social survey

For the training of field researchers/in depth interviewers for the main survey in social domain - preparation for field activities, contractor will organize two day training on february 16th-18th 2026. Training will attend around 190 participants. At the venue contractor is obliged to provide 2 full-board accommodation for participants, conference room usage with tables, speed internet and a sufficient number of standard power sockets for connecting laptops to electricity during work, coffee breaks (coffee, tea, water, juice), water in the work rooms, and travel expenses.

10.Training field researchers/in depth interviewers for one domain, economy component

For the training of field researchers/in depth interviewers for the main survey in economy domain - preparation for field activities, contractor will organize two day training on february 23th-25th 2026. Training will attend around 190 participants. At the venue contractor is obliged to provide 2 full-board accommodation for participants, conference room usage with tables, speed internet and a sufficient number of standard power sockets for connecting laptops to electricity during work, coffee breaks (coffee, tea, water, juice), water in the work rooms, and travel expenses.

11.Training of field researchers/in depth interviewers for one domain, environment component

For the training of field researchers/in depth interviewers for the main survey in environment domain- preparation for field activities, contractor will organize two day training on february 25th-27th 2026. In the same location as previous training (for economy domain). Training will attend around 190 participants. At the venue contractor is obliged to provide 2 full-board accommodation for participants, conference room usage with tables, speed internet and a sufficient number of standard power sockets for connecting laptops to electricity during work, coffee breaks (coffee, tea, water, juice), water in the work rooms, and travel expenses.

12.Evaluation meeting with field researchers/in depth interviewers to gather all information from the fieldwork

For evaluation meeting with field researchers/in depth interviewers after the fieldwork the contractor will organize one day meeting.  A Workshop will attend 185 participants for two day on march 30th - april 1st  2026. For the meeting, it is necessary to arrange full board accommodation for 2 nights for all participants. At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities, audio equipment and video projection devices. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

13.Workshop with SORS heads of departments and methodologists, regarding organization of upcoming activities on the DMSS LL development

For the workshop with SORS heads of departments and methodologists, regarding of organization of upcoming activities on the DMSS LL development contractor will organize four day workshop for 43 participants on April 6th-10th 2026. For the workshop, it is necessary to arrange full board accommodation for 4 nights for all participants. At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities, audio equipment and video projection devices. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

14.Workshops for presentation of main surveys for representatives of all local governments and regional CCIS offices

For the presentation of main surveys for representatives of all local governments and regional CCIS offices contractor will organize six one day workshops in 6 location on May 15th - 22th 2026 with the participation of top management from local governments and regional CCIS offices, involving around 195 persons (approximately 35 persons per location). At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities, audio equipment and video projection devices. It is also necessary to provide refreshment for all participants, which includes catering, bottled water during the work and two coffee breaks (coffee, tea, water, juice) for each location.

15.Workshop with SORS staff to discuss the local government and regional chambers of commerce opinion after the main survey

For the workshop with SORS, to discuss the local government and regional chambers of commerce opinion after the main survey contractor will organize a two-day workshop for 43 persons on June 3rd -5th 2026. For the meeting, it is necessary to arrange transport from Belgrade for around 20 persons and full board accommodation for 2 nights for all participants. At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities with enough table seats for all participants, audio equipment and video projection devices. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

16.Workshop with IT staff to discuss the local government and regional chambers of commerce opinion after the main survey

For the workshop with IT staff, to discuss the local government and regional chambers of commerce opinion after the main survey contractor will organize a two-day workshop for 37 persons on June 10th -12th 2026. For the meeting, it is necessary to arrange transport from Belgrade for around 25 persons and full board accommodation for 2 nights for all participants. At the venue contractor is obliged to provide technical conditions for the meeting: appropriate conference facilities with enough table seats for all participants, audio equipment and video projection devices. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

17. Training on how to use web portals and tools will be organized for all users

For the training on how to use web portal and tools, which will be organized for all users (354 participants) contractor must organize a two-day training on 24 locations for 354 participants (around 15 participants per location) in September – November 2027. SORS will provide all the equipment needed for the training by using laptops bought for use in Population 2022 and Agricultural census 2023. At the venue contractor is obliged to provide full board accommodation for 2 nights for all participants and technical conditions for the meeting:  conference room usage with tables, speed internet and a sufficient number of standard power sockets for connecting laptops to electricity during work and video projection devices. It is also necessary to provide refreshment for all participants, which includes bottled water during the work and two coffee breaks (coffee, tea, water, juice) for each location each day.

18. For the Decision-making Support System at the Local level visits, the contractor will organize four 3-day study visits in five different countries during 2025 and 2026, each for 5 participants. The contractor will be responsible for arranging transportation, accommodation, and insurance for all participants, covering a total of 3 nights per visit.- Listed in tables 4.2

Requested services for the Statistical Population Register (SPR)

1.Closing conference

For the Closing conference, where the SPR usability and project findings will be presented to the various stakeholders, statistics, the educational and scientific community, local self-government, etc, the contractor should organize a three-day event with approximately 80-100 participants in period october-december 2027. It is necessary to arrange transportation and full-board accomodation for 3 nights for all participants.

At the venue, the contractor is obligated to provide technical conditions for the conference: appropriate conference facilities, ensuring high-quality internet connectivity, setup of necessary audio-visual equipment (projectors, microphones, screens, speakers, etc.), on-site technical support to handle equipment and troubleshooting.

Also, it is necessary to provide bottled water for participants during the work and five servings for coffee breaks (coffee, tea, juice).

2.Workshops

For the planned Workshops, the contractor should organize two, three-day workshops with approximately 40 participants from SORS and various institutions responsible for managing administrative registers in the period june-december 2027. It is necessary to arrange transportation and full-board accomodation for 3 nights for all participants.

At the venue, the contractor is obligated to provide technical conditions for the workshop: appropriate conference facilities, ensuring high-quality internet connectivity, setup of necessary audio-visual equipment (projectors, microphones, screens, speakers, etc.), on-site technical support to handle equipment and troubleshooting.

Also, it is necessary to provide bottled water for participants during the work and five servings for coffee breaks (coffee, tea, juice).

3.Meetings

Organizing 10 single-day meetings with representatives of institutions responsible for managing administrative registers are planned in order to consider various methodological, organizational and technical issues regarding the SPR in the period june 2025-december 2027.

For each meeting, with approximately 60 participants, the overall costs comprises the usage of conference room which are fulfilling all technical conditions, catering services for the participants as well as bottled water for participants during the work and cofee break.

4.Training participants for the fieldwork

For the field assessmenet of the SPRS test database, a multi-stage trainings are planned. The first level represents the centralized training of 30 controllers (performed by the SORS staff) in the January-March 2027, while the second level is the training of 250 interviewers at several training points (conducted by the controllers and with the assistance of the SORS staff) in period January-March 2027.

It is necessary to arrange transportation and full-board accomodation for 3 nights for all participants (approximately 310 persons).

At the venue, the contractor is obligated to provide technical conditions for the training: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), ensuring high-quality internet connectivity, setup of necessary audio-visual equipment (projectors, microphones, screens, speakers, etc.), on-site technical support to handle equipment and troubleshooting.

Also, the refreshment should also be included (bottled water for participants during the work and coffee breaks).

5.Study visits

For the study visits to statistical institutes with experience in the field of development of statistical registers, the contractor should organize three, 3-day study visits (in three different countries) during 2025 and 2026, each for 5 participants. The contractor will be responsible for arranging international transportation, accommodation, and insurance for all participants, covering a total of 4 nights per visit.-

Listed in tables 4.2

Requested services for the  Labour Market Information System – LMIS

1.Preparatory workshop with SORS staff for developing LMIS For the organisational workshop with institutions and SORS staff for the upcoming activities contractor will organise 1 two-day workshop for around 60 participants up to 250 km from Belgrade in June or September-October 2025. For workshop it is necessary to arrange transport from Belgrade and full board accommodation for two nights for all participants. At the venue contractor is obliged to provide technical conditions for the training: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), with the high-speed internet, audio equipment and video projection devices, a sufficient number of standard power sockets for connecting laptops to electricity during work. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, and juice) for each day and one additional lunch.

2.Workshop to analyse survey results and define/calculate indicators

For the workshop of SORS staff contractor will organise 1 two-day workshop for around 20 participants up to 250 km from Belgrade in June or September-October 2025. For workshop it is necessary to arrange transport from Belgrade and full board accommodation for two nights for all participants. At the venue contractor is obliged to provide technical conditions for the training: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), with the high-speed internet, audio equipment and video projection devices, a sufficient number of standard power sockets for connecting laptops to electricity during work. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, and juice) for each day and one additional lunch.

3.Training of Interviewers, controllers, supervisors for the training of the interviewers, controllers, supervisors contractor will organise one two-day training in Belgrade or 250 km from Belgrade, for around 60 participants in December 2025. For the training, (if it is in Belgrade) it is necessary to arrange transport of approximately 50% of participants and full board accommodation for one (or two) nights. For other 50% participants (from Belgrade) one lunch should be provided.  In case of training out of Belgrade full board accommodation for one night and transport for all participants. At the venue contractor is obliged to provide technical conditions for the training: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), with the high-speed internet, audio equipment and video projection devices, a sufficient number of standard power sockets for connecting laptops to electricity during work. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, juice) for each day.

4.Meeting with the stakeholders to present survey results

For the Meeting with the stakeholders to present survey results contractor will organise 1 two-day meetings for around 30 participants up to 250 km from Belgrade in period May -October 2027. For meeting it is necessary to arrange transport from Belgrade and full board accommodation for two nights for all participants. At the venue contractor is obliged to provide technical conditions for the training: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), with the high-speed internet, audio equipment and video projection devices, a sufficient number of standard power sockets for connecting laptops to electricity during work. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, and juice) for each day and one additional lunch.

5.Training of LMIS users to use Web portal data and analysis

For the training of LMIS user’s contractor will organise 1 two-day event for around 110 participants up to 250 km from Belgrade in period October- December 2027. For training it is necessary to arrange transport from Belgrade and full board accommodation for two nights for all participants. At the venue contractor is obliged to provide technical conditions for the training: appropriate conference facilities (in the booked hotel or within walking distance from booked hotel), with the high-speed internet, audio equipment and video projection devices, a sufficient number of standard power sockets for connecting laptops to electricity during work. It is also necessary to provide bottled water for participants during the work and two coffee breaks (coffee, tea, water, and juice) for each day and one additional lunch.

6.  For the Decision-making Support System at the Labour Market Information System – LMIS, the contractor will organize three 3-day study visits in five different countries during 2025 and 2026, each for 5 participants. The contractor will be responsible for arranging transportation, accommodation, and insurance for all participants, covering a total of 3 nights per visit.- Listed in tables 4.2

## 4.3 Project management

### Responsible body

Project Management Team Statistical office Republic of Serbia

### Management structure

### Branko Josipović, director

### Project Management Team:

### Mira Nikić, Project Manager

### Olja Musić, Project Manager for Component I, Snežana Lakčević, Project Manager for Component II, Ljiljana Djordjević Project Manager for Statistical Population Register ( SPR), Jelena Suzić Project Manager for Decision-making Support System at the National level (DMSS NL), Nevena Mitrović Project Manager for Decision-making Support System at the Local level (DMSS LL), Vesna Pantelić Project Manager for Labour Market Information System – LMIS.

- LOGISTICS AND TIMING

## 5.1 Location

Belgrade, Northern and/or Central Serbia

## 5.2Start date & period of implementation of tasks

The intended start date is 01/06/2025 or till the finished international open tender procedure for this service and the period of implementation of the contract will be the end of 2027. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

- REQUIREMENTS

## 6.1Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

    - Key experts

Key experts

Key experts have a crucial role in implementing the contract. These Terms of Reference contain the required key experts’ profiles. The team of key experts shall ensure the provision of high-quality services throughout the assignment.  For each event at least one key expert will have to be responsible for all matters.

The tenderer shall submit CVs and Statements of Exclusivity and Availability for the following key experts:

Key expert 1: Team leader

The Project Coordinator will have at least the following tasks which may not be subcontracted:

1. Responsibility for the day-to-day management of the project and of each individual assignment.

2. Monitoring of the services rendered and of the performance of the service providers for the assignment.

3. Participation in meetings when required

Furthermore, the Project Coordinator must be employed by the Tenderer -Consortium Leader (no "free-lance").

Qualifications and skills

•Master’s or bachelor’s degree in marketing, communication, business, hospitality management or public relations, or a related field.

•Strong written and verbal communication skills in English and Serbian.

General professional experience

At least 8 years of professional experience related to organising of events at international level and in a multi-cultural environment.

Specific professional experience

•	At least 5 years of experience in management position (i.e. responsible of a team).

Key expert 2: Travel and events manager

Qualifications and skills

•Master or bachelor degree in marketing, communication, business, hospitality management or public relations, or a related field.

Strong written and verbal communication skills in English and Serbian

General professional experience

At least 5 years of professional experience related to organising of event and travel management services at international level and in a multi-cultural environment.

Specific professional experience

Certificate for international travel sales agent 4.6.1 or equivalent AMADEUS or GALILEO Certificate, references from previous projects on implemented services and work. Fluent knowledge of English and Serbian Language. Certificate for work in hotel reservation system, all major systems will be accepted.

Key expert 3: Financial manager

Qualifications and skills

•Master’s or bachelor’s degree in economics.

Strong written and verbal communication skills in English, Serbian and one more EU language

General professional experience

At least 5 years of professional experience related to financial tasks. Fluent knowledge of English and Serbian and one additional EU language.

Specific professional experience

Degree from Faculty of Economics, University of Serbia would be preferred. Fluent knowledge of English, Serbian and one more EU language is mandatory.

The contractor must provide proof:

• the educational and professional qualifications of the key expert and   staff member.

    - Other experts, support staff & backstopping

N/A

## 6.2Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## 6.3Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## 6.4Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

- REPORTS

## 7.1 Reporting requirements

The contractor will submit the following reports in English and Serbian language in one original.

- Interim Report for event on an annual basis, and it should include all events that took place in the previous year, and it must be submitted by January 31 of the current year for the previous year.

- Interim Report for airplane tickets and hotels in brought must be deliver after the finished service or on the months level. The interim report must be provided along with the corresponding invoice

- Final report with the same specifications as the interim report, incorporating any comments received from the contracting authority. The deadline for sending the final report is 10 days after finishing service-contract.

## 7.2Submission and approval of reports

The report referred to above must be submitted to the project manager identified in this Terms of Refference. The project manager is responsible for approving the reports.

- MONITORING AND EVALUATION

## 8.1Definition of indicators

N/A

## 8.2Special requirements

N/A